VIDEO PUBLISHING PROCESS

I	ENCODING

Activity Involved: encoding video to the five standard dcom sizes (st, hi, sm, sw, mp4)

Optional Services: editing, adding beginning or end slate, cropping, etc.

Person Involved: Eric Huff or Daniel Baldwin

Estimated time for Basic Service:  1 hour / per video (optional services not included); 30 mins / video for batch encoding

II 	VIDEO UPLOADING/PUBLISHING/METADATA TAGGING

Activities Involved: creating Segment Board item and XD#; creating filename and renaming the video; uploading video to streaming and/or progressive Limelight; creating and checking the links, creating icon art filename and submitting renamed clips to art team for icon creation, completing the metadata in the Segment Board, previewing video and tagging for appropriate keywords.

Person Involved: Josephine Atienza

Estimated Time: 20 mins. / video

III	COPY

Stage One – Writing

Activities Involved: previewing of video and creating both search and site copy

Persons Involved: Barbara Vay, Jessica Schwannhauser

Estimated Time: 15 – 20 mins. / video

Stage Two – Review

Activity Involved: editorial review and optional revision of the copy

Person Involved: Cathy Georges

Estimated Time: 5 - 10 mins. / video

IV	SEO REVIEW

Activity Involved: review search copy and keywords for SEO compliance

Person Involved: Jeff Preston

Estimated Time: 5 mins / video

V	QA REVIEW

Activity Involved: review all guest-facing copy for appropriateness.

Person Involved: Paula Shumard

Estimated Time: 5 mons / video

VI	CMS IMPORT

Activity Involved:  importing the Segment Board items plus all the links and data into the CMS.

Person Involved: Ryan Goldstein (DIMG-DOL BEER)

Estimated Time: 15 – 30 mins. / batch

Note:  This will eventually become automated and automatic, thus, can be included in the process without adding significant manhour.

Since the videos are processed individually, there is not much time difference if the videos are processed by batch, except for encoding and CMS import.

TO SUM UP:

1 – 5 VIDEOS:

Encoding:  			1 – 2 ½ hours

Uploading/Publishing/Tagging:	½ - 2 hours

Copy:				½ - 2 hours

SEO				< ½ hour

QA				< ½ hour

CMS Import			< ½ hour

TOTAL MANHOURS:		2 ½ - 8 hrs.

10 – 15 VIDEOS:

Encoding:  			5 - 7 hours

Uploading/Publishing/Tagging:	3 ½ - 5 hours

Copy:				3 ½ - 5 hours

SEO				1 hour

QA				1 hour

CMS Import			< ½ hour

TOTAL MANHOURS:		14 ½ - 19 ½ hrs.

20 – 25 VIDEOS

Encoding:  			10 – 12 ½ hours

Uploading/Publishing/Tagging:	6 - 8 hours

Copy:				6 - 8 hours

SEO				1 ½ - 2 hours

QA				1 ½ - 2 hours

CMS Import			< ½ hour

TOTAL MANHOURS:		25 ½ - 33 hrs.